## Development plan
Quotation Tool
Phase | Item # | Feature | Description / Notes | Status
| 0 | Separate tool from current SORP/POI tool | New tool version without regulatory SORP docs and custom analysis tools.
STAGE 1 — Core Features
| 1 | Basic PDF Personalised Quotation | Including policy details, fund projection, charges, selected funds, ESMA ratings
| 2 | Remuneration Statement | Commission details, amounts, clawback
| 3 | Ability to select Risk Rating for client | Select client risk rating based on risk profiling done elsewhere (risk profiling to come later)
| 4 | Portfolio Builder | Similar to what is developed so far, but tie fund choices more closely to risk profile. Separate asset classes.
| 5 | Add standard descriptions to document | Add PDC, tax details, disclaimers etc
| 6 | Add basic fund performances | Up to previous quarter end / year end?
| 7 | Cover Letter | Ability to add broker details?
| 8 | Statement of Suitability | Add it as editable text box that can be output in the PDF.
| 9 | Ability to select what to include in PDF output
| 10 | Glossary of terms in PDF Output
PHASE 2 — Advanced Features
Phase 2 | 1 | Add Risk Profiling Tool
| 2 | Add Retirement Income Calculator
| 3 | Add Fund Performances (auto update via API from FundFocus/AGI)
| 4 | Logins for broker to save their details | More complex — requires storing data.
| 5 | White Labelling — allow upload of broker logo etc | Possible without login but would require reupload each time.
| 6 | Factsheets | Need the equity exposure corrected before we include these.
| 7 | Tax Relief Illustrator for Contributions
| 8 | Backtest of Policy (Lookback Report) | Produces document showing how the investment would have done if invested on X date.